## 1 - Stakeholders info
STAKEHOLDER CLASSIFICATION
Based on Power-Interest Matrix: Supporter ¦ Leading ¦ Neutral ¦ Resistant
# | Stakeholder | Role | Power | Interest | Quadrant Strategy | Current Classification | Desired Classification
▶ RESISTANT — Actively or passively opposed; require targeted engagement to convert
1 | Local Municipality | Permits & compliance approvals | High | Medium | Manage Closely | Resistant | Supporter
2 | Employees | End users of new HQ facility | Low | High | Empower Engage | Resistant | Supporter
3 | Union Representatives | Employee rights & labour relations | Medium | High | Keep Informed | Resistant | Supporter
4 | Community Neighbors | Local community & neighbourhood impact | Low | Medium | Minimal Effort | Resistant | Neutral
▶ LEADING — Influential, may be driving agenda; align their goals with project success
1 | CFO | Oversees cost control & rent negotiation | High | Medium | Keep Satisfied | Leading | Supporter
2 | CEO | Strategic oversight & final authority | High | Medium | Keep Satisfied | Leading | Supporter
3 | Customer Service Head | Client seat provisioning & continuity | Medium | High | Keep Informed | Leading | Supporter
4 | Landlord | Lease terms & site access | High | High | Manage Closely | Leading | Supporter
▶ NEUTRAL — Neither for nor against; low engagement risk but should be cultivated
1 | Procurement Manager | Vendor contracts & compliance | Medium | Medium | Monitor | Neutral | Supporter
2 | Sales Head | Client communication & pipeline protection | Medium | Medium | Monitor | Neutral | Supporter
3 | Moving Company | Physical relocation of assets | Low | Medium | Minimal Effort | Neutral | Supporter
4 | Furniture Supplier | New office furniture & fitout supply | Low | Medium | Minimal Effort | Neutral | Supporter
5 | Security Provider | Access control & physical security | Low | Medium | Monitor | Neutral | Supporter
6 | External Auditors | Financial compliance review | High | Medium | Keep Satisfied | Neutral | Supporter
7 | Insurance Provider | Risk & asset coverage during move | Medium | Medium | Keep Satisfied | Neutral | Supporter
8 | Backup Vendors | Contingency supply chain | Low | Medium | Minimal Effort | Neutral | Supporter
▶ SUPPORTER — Actively supporting the project; maintain and leverage their support
1 | COO (Sponsor) | Approves scope, budget & timeline | High | High | Manage Closely | Supporter | Supporter
2 | HR Director | Employee relocation & change management | Medium | High | Keep Informed | Supporter | Supporter
3 | IT Director | IT migration & business continuity | High | High | Manage Closely | Supporter | Supporter
4 | Facilities Manager | Fit-out, space planning & site coord. | Medium | High | Keep Informed | Supporter | Supporter
5 | Finance Lead | Accounting consolidation & cost tracking | Medium | High | Keep Informed | Supporter | Supporter
6 | Project Manager | Overall project coordination & reporting | High | High | Manage Closely | Supporter | Supporter
7 | Assistant PM | Documentation & reporting support | Low | High | Empower Engage | Supporter | Supporter
8 | IT Migration Vendor | System & data migration execution | Medium | High | Keep Informed | Supporter | Supporter
9 | Telecom Provider | Connectivity & telephony setup | Medium | High | Keep Informed | Supporter | Supporter
10 | Key Customers | Beneficiaries of improved service capacity | Medium | High | Empower Engage | Supporter | Supporter
11 | Account Managers | Client satisfaction & feedback | Medium | High | Keep Informed | Supporter | Supporter
12 | Change Champions | Employee adaptation & peer support | Low | High | Empower Engage | Supporter | Supporter
CLASSIFICATION SUMMARY
Supporter | 12
Leading | 4
Neutral | 8
Resistant | 4

## 2 - Power-Interest Analysis
POWER / INTEREST ANALYSIS & STRATEGY
Each stakeholder is mapped by Power × Interest — determining the management strategy
QUADRANT STRATEGY REFERENCE
Strategy | Power | Interest | Guidance
Manage Closely | High | High | Core team — involve in all key decisions and milestone reviews
Keep Satisfied | High | Low/Med | High power but lower day-to-day interest — keep updated, avoid surprises
Keep Informed | Low/Med | High | High interest but limited power — regular comms to maintain engagement
Empower Engage | Low | High | Enthusiastic supporters — empower to champion the project internally
Monitor | Low/Med | Low/Med | Watch passively — minimal active management needed
Minimal Effort | Low | Low | Peripheral — only engage when operationally necessary
POWER × INTEREST MATRIX — Stakeholder Placement
Power \ Interest | Low Interest | Medium Interest | High Interest
High Power | ▶ Keep Satisfied | ▶ Keep Satisfied • CFO • CEO • Local Municipality • External Auditors | ▶ Manage Closely • COO (Sponsor) • IT Director • Project Manager • Landlord
Medium Power | ▶ Monitor | ▶ Monitor • Procurement Manager • Sales Head • Insurance Provider | ▶ Keep Informed • HR Director • Facilities Manager • Finance Lead • Customer Service Head • IT Migration Vendor • Telecom Provider • Key Customers • Account Managers • Union Representatives
Low Power | ▶ Minimal Effort | ▶ Minimal Effort • Moving Company • Furniture Supplier • Security Provider • Community Neighbors • Backup Vendors | ▶ Empower Engage • Assistant PM • Employees • Change Champions

## 3 - Engagement Plan
STAKEHOLDER ENGAGEMENT PLAN — HQ Relocation Project
Goal: Convert Resistant & Neutral to Supporter ¦ Align Leading ¦ Maintain Supporters
# | Stakeholder | Current Status | Goal | Main Challenge | Engagement Approach | Actions | Channel | By When
⚠ PRIORITY 1 — Convert RESISTANT to SUPPORTER
1 | Local Municipality | Resistant | Supporter | Slow permit approvals may delay the project | Build a cooperative relationship early | 1. Submit all permits 8 weeks ahead of schedule 2. Set up a dedicated legal liaison for all contacts 3. Send a monthly compliance update 4. Hold a pre-submission meeting to align expectations | Formal meetings + Written reports | Month 1
2 | Employees | Resistant | Supporter | Concerns about commute changes and the new space | Listen, inform, and involve them early | 1. Hold a company-wide town hall to explain the move benefits 2. Launch an FAQ page with an open Q&A option 3. Offer site preview visits before the move 4. Provide a transport or relocation allowance 5. Run weekly pulse surveys and act on the feedback | Town Hall + Email + Intranet | Month 1
3 | Union Representatives | Resistant | Supporter | Concerns about employee rights and consultation process | Involve them early with full transparency | 1. Brief union reps before any public announcement 2. Share the relocation policy draft for joint review 3. Invite them to relevant planning meetings 4. Put all commitments in writing 5. Hold a formal monthly check-in throughout the project | Formal meetings + Written commitments | Month 1
4 | Community Neighbors | Resistant | Supporter | Concerns about noise, traffic, and local disruption | Be transparent and show consideration | 1. Send a notice letter 6 weeks before the move 2. Share the traffic and noise management plan 3. Assign a single point of contact for community queries 4. Run a small CSR gesture such as a local clean-up or sponsorship 5. Send a thank-you note after the move | Written notice + Community board | Pre-move
★ PRIORITY 2 — LEADING stakeholders: Maintain their position and alignment
1 | CFO | Leading | Maintain Leading | Cost-focused; may push back if budget is under pressure | Keep them informed with clear financial data | 1. Build and share a live cost dashboard together 2. Present a cost-benefit summary in the first month 3. Report any budget risk within 24 hours 4. Involve them in all lease negotiation milestones 5. Proactively highlight cost savings each month | Dashboard + Monthly meeting | Month 1
2 | CEO | Leading | Maintain Leading | May disengage if progress is not clearly tied to strategy | Keep it concise and strategic | 1. Send a one-page executive summary every quarter 2. Lead all updates with strategic and business benefits 3. Flag CEO-level decisions well in advance 4. Invite the CEO to key milestone moments 5. Align all project messaging to the company vision | Executive brief + Quarterly meeting | Ongoing
3 | Customer Service Head | Leading | Maintain Leading | Worried about client seating capacity and service continuity | Show them the plan and involve them in it | 1. Share a detailed seating plan with clear client capacity 2. Include them in space planning sessions 3. Present the service continuity plan for move day 4. Send a weekly operations dashboard | Dashboard + Weekly meeting | Month 2
4 | Landlord | Leading | Maintain Leading | May use lease terms as leverage if they feel uninformed | Treat them as a project partner, not just a landlord | 1. Share the project timeline at the start of the lease 2. Hold a monthly progress meeting 3. Involve CFO and legal in all negotiation points 4. Flag any access or fit-out changes early 5. Provide formal handover documentation at project close | Formal meetings + Reports | Ongoing
◆ PRIORITY 3 — Convert NEUTRAL to SUPPORTER
1 | Procurement Manager | Neutral | Supporter | Low engagement may allow SLAs to slip | Give them clear ownership and involve them more | 1. Invite them to bi-weekly milestone reviews 2. Assign them as owner of the vendor SLA tracker 3. Share a procurement dashboard with the PM weekly 4. Acknowledge their work in project updates | Tracker + Bi-weekly meeting | Month 1
2 | Sales Head | Neutral | Supporter | Sees the move as a distraction from revenue targets | Connect the move to business growth | 1. Present the new HQ as a sales and client asset 2. Involve them in the client communication plan 3. Share the client expansion seating layout 4. Send a monthly update linking the move to the business pipeline | Monthly report + Meeting | Month 2
3 | Security Provider | Neutral | Supporter | Risk of missing commissioning deadlines if not tracked | Set clear deliverables and check in regularly | 1. Lock in the access system commissioning date in the contract 2. Hold a monthly progress call 3. Include them in the final site readiness walkthrough 4. Send a deliverables checklist 4 weeks before go-live | Monthly call + SLA document | Month 3
4 | External Auditors | Neutral | Supporter | Need assurance that financial controls are in place | Provide clear and timely financial reporting | 1. Share the relocation financial controls framework early 2. Include them in the quarterly risk review 3. Maintain a full audit trail of all project spend 4. Report any compliance event within 48 hours | Quarterly report + Meeting | Ongoing
5 | Insurance Provider | Neutral | Supporter | May be unaware of the move — policy gap risk | Notify early and confirm full coverage | 1. Notify the insurer of the move date and scope immediately 2. Confirm all assets are covered during transit 3. Get written confirmation of coverage 4. Share the final asset list before move day | Formal letter + Meeting | Month 1
6 | Moving Company | Neutral | Supporter | Execution risk if the brief is not clear | Give them everything they need to succeed | 1. Provide the full asset list and floor plan 4 weeks in advance 2. Run a joint site walkthrough before the move 3. Agree a detailed move schedule with buffer days 4. Hold a daily check-in during the move phase 5. Sign off against the asset list after the move | Daily call (move phase) + Logistics doc | Move phase
7 | Furniture Supplier | Neutral | Supporter | Delivery delays could hold up the fit-out | Manage through contract SLAs and regular tracking | 1. Include a delivery SLA with a penalty clause in the contract 2. Review the delivery schedule weekly 3. Agree an escalation contact upfront 4. Confirm the final delivery date 2 weeks before the move | Weekly update + Contract SLA | Pre-move
8 | Backup Vendors | Neutral | Supporter | Not engaged — activation delay if the primary vendor fails | Pre-qualify and have them ready to go | 1. Pre-qualify all backup vendors by Month 2 2. Confirm SLAs in writing 3. Brief them on the project timeline so they are ready to activate 4. Check readiness monthly | Written SLA + Periodic check | Month 2
✔ MAINTAIN — Keep SUPPORTERS engaged and on side
1 | COO (Sponsor) | Supporter | Supporter | Risk of losing focus if not kept closely involved | Keep the sponsor visible and in control | 1. Hold bi-weekly milestone reviews with a clear status report 2. Escalate any blockers within 24 hours 3. Mark milestones with a formal acknowledgement 4. Involve in the new HQ launch announcement | Meeting + Executive report | Ongoing
2 | IT Director | Supporter | Supporter | High delivery pressure — risk of scope drift | Support them with clear governance | 1. Weekly migration meeting with a live issues log 2. Document the rollback plan by Month 2 3. Run a full connectivity test 2 weeks before go-live 4. Hold a post-migration lessons-learned session | Weekly meeting + Report | Ongoing
3 | HR Director | Supporter | Supporter | Needs enough resources to manage change at scale | Empower and resource adequately | 1. Allocate a dedicated change management budget 2. Hold a weekly HR sync with the PM 3. Share pulse survey results to adapt messaging 4. Recognise the HR team's contribution in project comms | Weekly sync + Town hall | Ongoing
4 | Facilities Manager | Supporter | Supporter | Risk of overload during the fit-out phase | Structured site oversight | 1. Weekly site visit with the PM 2. Shared snag log reviewed at every visit 3. Clear sign-off checklist before go-live 4. Build a buffer week into the fit-out timeline | Weekly site visit + Report | Ongoing
5 | Project Manager | Supporter | Supporter | Single point of failure risk for the whole project | Strong governance and a backup plan | 1. Weekly steering committee with the exec sponsor 2. Maintain a live RAID log at all times 3. Document all decisions in writing 4. Ensure the Assistant PM can cover if needed | Weekly steering + Dashboard | Ongoing
6 | Assistant PM | Supporter | Supporter | Needs clear direction to stay on top of tasks | Give clear ownership and daily alignment | 1. Daily stand-up to align on priorities 2. Assign ownership of the action log and status reports 3. Provide regular feedback and recognition | Daily stand-up | Ongoing
7 | Finance Lead | Supporter | Supporter | Needs clean data from the project for reporting | Structured and timely cost reporting | 1. Weekly cost update shared with the PM 2. Maintain a shared live cost tracker 3. Flag any variance on the same day it is identified | Weekly report + Tracker | Ongoing
8 | IT Migration Vendor | Supporter | Supporter | External party — quality depends on daily management | Daily oversight during the migration window | 1. Daily call during the cutover period 2. Agree clear KPIs for migration success 3. Document rollback triggers in writing 4. Issue a post-migration sign-off report | Daily call + Technical report | Migration phase
9 | Telecom Provider | Supporter | Supporter | Connectivity is critical from day one — no room for delay | Manage readiness closely against SLA | 1. Weekly readiness report 2. Full connectivity test 2 weeks before go-live 3. On-site engineer present on move day 4. Escalation contact agreed in the contract | Weekly report + On-site test | Ongoing
10 | Key Customers | Supporter | Supporter | Need assurance that service will not be disrupted | Proactive and positive client communication | 1. Notify key clients 8 weeks before the move 2. Provide a dedicated client liaison contact 3. Send a quarterly satisfaction survey 4. Host a post-move showcase of the new space | Quarterly survey + Email | Ongoing
11 | Account Managers | Supporter | Supporter | Front-line with clients — need consistent messaging | Keep them briefed and ready to respond | 1. Provide a client FAQ script covering the move 2. Send a weekly internal update before any client-facing comms 3. Give a clear escalation path for client concerns | Weekly briefing + Email | Ongoing
12 | Change Champions | Supporter | Supporter | Volunteer role — risk of disengagement if not valued | Recognise their contribution and keep them energised | 1. Weekly HR workshop to equip them with the latest info 2. Give them early access to site news to share with peers 3. Name them publicly in all-staff communications 4. Host a celebration event for champions after the move | Weekly workshop + Comms | Ongoing